## Contract Log
CONTRACT LOG
When to use: A useful tool to have at the front of your contract file. Notates the contract actions, communications and balance of the contract.
Contract: | IT Services Contract # 16-0945
Contractor: | Computer Services, Inc.
Date | Action | Description | $ | Contract Balance
2015-02-01 | Base Funding for Year 1 |  |  | 160000
2015-03-05 | Pre-Commencment Meeting | Met w Contractor, AG, and Division Mgr to go over quality assurance procedures for the contract. Refer to Minutes in Tab C.
2014-03-25 | Telephone Call w Mr. Contractor | Mr. Contractor and team added an extra 5 hours of work required for Sprint #1. He confirmed that these hours would be taken off of next month's hour pool.
2015-03-31 | Invoice #20001 for March | 65hrs @ $320/hr | 20800 | 139200
2015-04-29 | Email from Mr. Contractor | Mr. Contractor was only able to make up 2 out of the 5 hours from last month, have email Ms. Spot, my supervisor
2015-04-30 | Invoice #20002 for April | 58hrs @ $320/hr | 18560 | 120640
2015-05-15 | Stakeholder Meeting | Met w Contractor, and Division Mgr on current sprint surge requirement. Contractor estimates an extra 30 hours per month needed to develop code on deadline. Procurement Officer approved this change (Refer to Memo for Record in File - Tab D)
2015-05-30 | Invoice #20003 for May | 90hrs as approved on 5/15/15 | 28800 | 91840
2015-06-01 | Modification 001: Rate Change to $350/hr | Modification to add funds and rate per hour for A Team Coders as approved by MFR (Tab E) | 24000 | 115840
| TOTALS |  | 92160

## Burn Rate Log
BURN RATE LOG
When to use: When you have a service contract with estimated labor hours for the period. This Log assists the Procurement Specialist in seeing where the contract is burning too high and additional funds or a decrease in scope may be required.
Contract: | IT Services Contract # 16-0945
Contractor: | Computer Services, Inc.
Date | Description | Estimated Hours | Estimated Rate/hr | Est $ | Actual Hours | Actual Rate/hr | Actual $ | Under / (Over) Variance | Contract Balance | Notes
2015-02-01 | Base Funding | [7 empty] | 160000
2015-03-01 | IT Services & Maintenance | 60 | 320 | 19200 | 65 | 320 | 20800 | -1600 | 139200
2015-04-01 | IT Services & Maintenance | 60 | 320 | 19200 | 58 | 320 | 18560 | 640 | 120640
2015-05-01 | IT Services & Maintenance | 60 | 320 | 19200 | 90 | 320 | 28800 | -9600 | 91840 | Sprint had to be reperformed
2015-06-01 | IT Services & Maintenance | 60 | 320 | 19200 | 90 | 320 | 28800 | -9600 | 63040 | Additional sprints added to scope
2015-06-01 | Modification 001: Rate Change to $350/hr | [5 empty] | 24000 |  | 87040 | Additional funds for sprints and rates increase
2015-07-01 | IT Services & Maintenance | 60 | 320 | 19200 | 85 | 350 | 29750 | -10550 | 57290
2015-08-01 | IT Services & Maintenance | 60 | 320 | 19200 | 85 | 350 | 29750 | -10550 | 27540
2015-09-01 | IT Services & Maintenance | 60 | 320 | 19200 | 85 | 350 | 29750 | -10550 | -2210
2015-10-01 | IT Services & Maintenance | 60 | 320 | 19200
2015-11-01 | IT Services & Maintenance | 60 | 320 | 19200
2015-12-01 | IT Services & Maintenance | 60 | 320 | 19200
| TOTAL FOR YEAR 1 | 420 |  | 134400 | 558 |  | 210210
Data
Date | Sum of Est $ | Sum of Actual $
Feb 01
Mar 01 | 320 | 65
Apr 01 | 320 | 58
May 01 | 320 | 90
Jun 01 | 320 | 90
Jul 01 | 320 | 85
Aug 01 | 320 | 85
Sep 01 | 320 | 85
Total Result | 2240 | 558